## App Changelog & PM
Maritime PMS - Data Ingestion Tool
Project Management Change Log - August 2026 (Recent Tasks & Deployments)
Task ID | Feature / Area | Commit | Date Completed | Description of Change | Technical Details / Files | Deployment Status | Impact / Business Value
TASK-001 | SharePoint Ingestion | 788085f | 2026-08-28 | Single-File SharePoint Ingestion Support | Modified list_folder_contents_v2 in sharepoint.py to check if a share link resolves directly to a file instead of a folder, returning it as a single-item tree. | Deployed to Production | Enables users to paste a direct SharePoint sharing link for a single file, eliminating the need to sync full folders or navigate a file tree.
TASK-002 | Manuals UI | c4be931 | 2026-08-28 | SharePoint Original File Badge Link | Added sharepoint_path metadata properties to Manual frontend interface and rendered a styled 'SharePoint Original' link badge in the table. | Deployed to Production | Allows users to click directly from the tool to open and download the original, un-flattened manual file from SharePoint.
TASK-003 | Ingestion UI | c729c94 | 2026-08-28 | SharePoint Sessions History & Auto-restore Tab | Rendered recent sessions history inside Step 1 layout on Ingestion page. Configured tab state to switch to 'SharePoint' and 'Step 3' automatically on mount if active session exists. | Deployed to Production | Restores visibility of background imports on page load and allows navigation/retry for previous sessions directly without reconnecting.
TASK-004 | Extraction | 6f29bd7 | 2026-08-28 | Target-Respecting Single Page Retry Ingestion | Updated /page-status resolver in ingestion.py to skip resolving default classification ranges if any physical columns have been customized. | Deployed to Production | Prevents running unwanted extractions (e.g. running components extraction on a spares-only page) when retrying a single page, saving API tokens.
TASK-005 | Manuals | 4476c45 | 2026-08-28 | Custom Field Fallback Fix in Gap Report | Modified get_no_extracted_records_report in manuals.py to check has_custom_refs. Avoids defaulting to all-page classifications when user explicitly leaves columns blank. | Deployed to Production | Eliminates false alarms in the 'No Extracted Records' warning report by respecting empty cells as intentional user selections.
TASK-006 | Manuals UI | 1cab85d | 2026-08-27 | 'No Extracted Records' Report & Auto-Popup Modal | Added GET /no-extracted-records endpoint. Created NoExtractedRecordsModal JSX grid. Configured automatic useEffect popup on extraction completion. | Deployed to Production | Instantly warns the user when targeted pages return zero extractions from Claude so they can inspect discrepancies immediately.
TASK-007 | Manuals UI | d6dedb6 | 2026-08-27 | Instant Data Refresh in Page Status Modal | Added useEffect query invalidation trigger on manualId change inside ManualPageStatusModal.tsx. | Deployed to Production | Bypasses stale React Query cache to load fresh, up-to-date page progress data immediately on modal open.
TASK-008 | Text Extraction | 35c4e42 | 2026-08-27 | Iterative Page-by-Page Saves & Detailed Progress | Refactored auto_extract_from_manual to run _process_and_save_page_records page-by-page. Added detailed download/pre-processing text logs to progress status updates. | Deployed to Production | Prevents data loss from server crashes during long runs, and provides step-by-step transparency on active extraction phases.
TASK-009 | Text Extraction | 28bd76f | 2026-08-27 | Selective Single-Page Text Extraction Pre-Filtering | Integrated page_numbers filter inside type_to_text compilation loop in extractor.py. | Deployed to Production | Saves LLM input costs and increases processing speed by sending only text of targeted pages during retries.
TASK-010 | Extraction UI | 7a52ff6 | 2026-08-26 | Stop Extraction & Stop Ingestion Handlers | Created stop endpoints in backend and added stop cancellation checks to background tasks. Added 'Stop' buttons on the UI progress bars. | Deployed to Production | Empowers users to halt hung extraction runs or clear queues immediately.
TASK-011 | Data Matching | 32fbc05 | 2026-08-25 | Flame Eye Synonym Library Matching | Updated global job library synonym mappings to match variations like Boiler Flame Eye and Main Burner. | Deployed to Production | Increases matching accuracy for specialized vessel boiler components.
TASK-012 | Database | 9d389e3 | 2026-08-25 | Auto-Reset of Stuck Ingestions on Boot | Added startup check to reset manuals in 'running' or 'screening' back to failed/queued. Added automatic data recovery for M-29 volume 2. | Deployed to Production | Maintains database integrity and clears queue lockups after container restarts.